## Project General Info
Team |  | 1 |  |  |  | Tên thành viên | Nguyễn Quang Tuyến | Đỗ Đăng Khoa | Nguyễn Văn Huy | Cao Văn Lâm
Topic |  | Hotel management system |  |  |  | Mã thành viên | TuyenNQ | KhoaDD | HuyNV | LamCV
No | Actor |  | Feature Code | Feature Name | Description | Member In Charge |  |  | In Charge Iteration |  | Development Status |  |  |  |  | Update | Update Detail
[11 empty] | Searching (S) | In Progress (IP) | Done (D) | Test (T) | Finished Deploy (FD)
1 | Manager |  | Staff_Management | Manage Staff(View List) | Displays a list of all the staff members in the system | KhoaDD |  |  | Sprint 3 | [5 empty] | x
2 | Manager |  | Staff_Management | Manage Staff (View Detail) | Provides detailed information about a selected staff member. | KhoaDD |  |  | Sprint 3 | [5 empty] | x
3 | Manager |  | Staff_Management | Manage Staff (Add Staff) | Allows the addition of a new staff member to the system. | KhoaDD |  |  | Sprint 3 | [5 empty] | x
4 | Manager |  | Staff_Management | Manage Staff (Edit Staff) | Enables editing or updating of a staff member’s details. | KhoaDD |  |  | Sprint 3 | [5 empty] | x
5 | Manager |  | Staff_Management | Manage Staff (Delete Staff) | Removes a staff member from the system. | KhoaDD |  |  | Sprint 3 | [5 empty] | x
6 | Customer |  | Bill | Bill | Manages billing information or displays billing-related features. | KhoaDD |  |  | Sprint 3 | [5 empty] | x
7 | User |  | User_Login | Login | Allows existing users to log into the system | HuyNV |  |  | Sprint 3 | [5 empty] | x
8 | User |  | User_Register | Register | Facilitates the registration of new users into the system. | HuyNV |  |  | Sprint 3 | [5 empty] | x
9 | Manager |  | Customer_Management | Manage Customer ( Delete User) | Deletes a customer’s account from the system. | HuyNV |  |  | Sprint 3 | [5 empty] | x
10 | Manager |  | Customer_Management | Manage Customer ( View Customer) | Displays the details of a customer. | HuyNV |  |  | Sprint 3 | [5 empty] | x
11 | Manager |  | Customer_Management | Manage Customer (Update Customer) | Updates the information of a customer in the system | HuyNV |  |  | Sprint 3 | [5 empty] | x
12 | User |  | User_UpdateProfile | Update Profile | Allows users to update their own profile details. | HuyNV |  |  | Sprint 3 | [5 empty] | x
13 | Customer |  | Service | Request service | Enables customers to request a service from the hotel. | LamCV |  |  | Sprint 3 | [5 empty] | x
14 | Manager |  | Service | Add new service | Adds a new service offering to the hotel system. | LamCV |  |  | Sprint 3 | [5 empty] | x
15 | Manager |  | Service | Edit service | Allows modification or updating of an existing service. | LamCV |  |  | Sprint 3 | [5 empty] | x
15 | Manager |  | Service | Add service item to service | Add new service item to service | LamCV |  |  | Sprint 3 | [5 empty] | x
15 | Manager |  | Service | Delete service item | Delete service item from service list | LamCV |  |  | Sprint 3 | [5 empty] | x
15 | Manager |  | Service | Delete service | Remove service from service list | LamCV |  |  | Sprint 3 | [5 empty] | x
16 | Customer |  | Booking | Create booking | Facilitates the creation of a new room booking. | TuyenNQ |  |  | Sprint 3 | [5 empty] | x
17 | Customer |  | Booking | View booking information | Displays details of a particular room booking. | TuyenNQ |  |  | Sprint 3 | [5 empty] | x
18 | Customer |  | Booking | Change booking information | Allows modifications to an existing room booking. | TuyenNQ |  |  | Sprint 3 | [5 empty] | x
19 | Customer |  | Booking | Cancel Booking | Cancels a customer’s room booking. | TuyenNQ |  |  | Sprint 3 | [5 empty] | x
20 | Manager |  | Room_Management | Add room | Adds a new room to the hotel system. | TuyenNQ |  |  | Sprint 3 | [5 empty] | x
21 | Manager |  | Room_Management | View room information | Displays information about a specific room. | TuyenNQ |  |  | Sprint 3 | [5 empty] | x
22 | Manager |  | Room_Management | Delete room | Removes a room from the hotel system. | TuyenNQ |  |  | Sprint 3 | [5 empty] | x
23 | Manager |  | Room_Management | View all room category | Shows all available room categories in the hotel. | TuyenNQ |  |  | Sprint 3 | [5 empty] | x
24 | Manager |  | Room_Management | Add room category | Adds a new category of rooms to the system. | TuyenNQ |  |  | Sprint 3 | [5 empty] | x
25 | Manager |  | Room_Management | Edit room category | Allows modification of an existing room category. | TuyenNQ |  |  | Sprint 3 | [5 empty] | x
26 | Manager |  | Room_Management | Delete room category | Removes a room category from the system. | TuyenNQ |  |  | Sprint 3 | [5 empty] | x