## Project Calendar
Mock Project Master Plan
Group 2: Riconrinhau
Date | State | Lesson /Topic /Module /Working Item | Trainer / PIC | Notes (logistic, materials..)
2024-09-04 | Initiation | Kick off meeting | TamTTT + SV
2024-09-05 |  | Create team + create team plan + team meeting | SV
2024-09-06 |  | Read/Edit requirement + Create requirement outline + Figma | SV
2024-09-09 |  |  | SV
2024-09-10 |  |  | SV
2024-09-11 |  | Review/Edit requirement + finalize requirement | SV
2024-09-12 |  | Edit SRS + Design framework + Create CSS | SV
2024-09-13 |  | Final Review SRS + Review framework + CSS + Final Figma | SV
2024-09-16 | Sprint 1 | DD-Design-Blackbox Testing-Coding-QA for Feature phase 1 | SV
2024-09-17 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 1 | SV
2024-09-18 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 1 | SV
2024-09-19 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 1 | SV
2024-09-20 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 1 | SV
2024-09-23 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 1 | SV
2024-09-24 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 1 | SV
2024-09-25 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 1 | SV
2024-09-26 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 1 | SV
2024-09-27 |  | Review sprint 1- Feedback - Start plan for sprint 2 | SV
2024-09-30 | Sprint 2 | DD-Design-Blackbox Testing-Coding-QA for Feature phase 2 | SV
2024-10-01 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 2 | SV
2024-10-02 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 2 | SV
2024-10-03 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 2 | SV
2024-10-04 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 2 | SV
2024-10-07 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 2 | SV
2024-10-08 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 2 | SV
2024-10-09 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 2 | SV
2024-10-10 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 2 | SV
2024-10-11 |  | Review sprint 2- Feedback - Start plan for sprint 3 | SV
2024-10-14 | Sprint 3 | DD-Design-Blackbox Testing-Coding-QA for Feature phase 3 | SV
2024-10-15 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 3 | SV
2024-10-16 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 3 | SV
2024-10-17 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 3 | SV
2024-10-18 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 3 | SV
2024-10-21 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 3 | SV
2024-10-22 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 3 | SV
2024-10-23 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 3 | SV
2024-10-24 |  | DD-Design-Blackbox Testing-Coding-QA for Feature phase 3 | SV
2024-10-25 |  | Review product- Maintain- Feedback | SV
2024-10-28 | Final phase | Maintain-Update- Prepare for presentation | SV
2024-10-29 |  | Maintain-Update- Prepare for presentation | SV
2024-10-30 |  | Final Release | TamTTT + SV
Formulas:
Date = IF(WEEKDAY([Date, row above])=6,[Date, row above]+3,[Date, row above]+1)